## Files to change
Multi-user sign-in: files to change
Extreme & Change Analytics Lab. Status column: pick To do / In progress / Done.
File | Type | Change | Status
app\security.py | Changed | Sign-in page gets a user name field; checks user name + password; adds 'Signed in as ...' and per-user lockout | To do
app\users.py | New | Reads users from users.json, with hashed passwords and roles | To do
tools\manage_users.py | New | Add, remove, reset, disable and list users | To do
tests\test_users.py | New | Tests for multi-user sign-in | To do
config.ini | Changed | One new setting: where users.json is (no secrets) | To do
.gitignore | Changed | Adds users.json so it is never committed | To do
Docs (scripts_reference.docx) | Changed | New section on managing users | To do

## Not touched
Not touched by this change
These parts of the app stay exactly as they are.
Component | Files
Analysis engine | app\services\extreme_change_engine.py
Data loader | app\services\data_loader.py
Chart explorer | app\static\js\chart_explorer.js
Data listing | app\static\js\data_listing.js
AI report | app\services\report_*.py, app\static\js\ai_report.js
Database script | database\tables\titanium_analytics_history.sql

## Rollout steps
Rollout steps
The current shared password keeps working until the first user is added (no downtime).
# | Where | Step | Commands | Status
1 | PC | Extract the update, run the tests, test locally with login | .\test_all.ps1 -SkipExe .\start.ps1 -Secure | To do
2 | PC | Build the package and copy both files to the server | .\make_server_zip.ps1 | To do
3 | Server | Deploy, then add a user for each person | .\deploy_windows_server.ps1 -Domain app.titaniumanalyses.com .\.venv\Scripts\python.exe tools\manage_users.py add <name> | To do
4 | PC | Commit and push | git add -A git commit -m "Multi-user sign-in" git push origin dev | To do
|  | Steps done | 0 of 4
|  | Files done (sheet 'Files to change') | 0 of 7

## Open questions
Open questions before building
Fill in the Answer column (example: 5 users / roles: yes / file).
Question | Answer | Notes
How many users? |  | Roughly how many people will sign in
Roles (admin / user) or same access for everyone? |  | Admins could e.g. be the only ones generating AI reports
Users stored in a file on the server or in SQL Server? |  | File is simplest to start; SQL Server can record who created each run/report